## Feuil1
Project Plan Chemistry 4P
| Task | Name | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11
| 1. Project plan draft | W, A, J, S
| 2. Project plan final | W, A, J, S
3. Analysing the best-performing MOFs for He/N2 separation given in the literature
Grand canonical Monte Carlo (GCMC) simulations to find the best-performing MOFs for He separation
Calculation of the amount of gas adsorbed using grand canonical Monte Carlo (GCMC) simulations
Computation of Henry's constants using the Widom insertion method
Finding the best-performing MOFs for He separation from natural gases from the CCD MOF database
Comparison with the MOFs from the literature, finding similarities/differences
Study of the chemical properties required for efficient He sepation
Study of the strip of He from the MOFs and the stability of the structures under strip conditions
Sustainability analysis to determine stability under these conditions
Comparison of predictions of molecular simulations with the experimentally available data for He permeability of several MOF membranes
Comparison of the selectivity and permeability of the MOF membranes with those of traditional polymer and zeolite membranes
Calculation of pore volumes, densities, surface areas, limiting pore diameters (LPDs) and largest cavity diameters (LCDs) of best-performing MOFs
Calculation of the different API for best-performing MOFs